Refer to the Annotated Annual Planning Calendar for detailed information

| Meetings & Data | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Data prep to get ready for meetings (run data reports, update graphs, prepare visuals) |  |  | 10/6 | 11/10 | 12/8 | 1/12 | 2/9 | 3/9 | 4/13 | 5/11 | 6/17 |
| Leader meeting to prepare for the team meeting |  |  | 10/8 | 11/12 | 12/10 | 1/14 | 2/11 | 3/11 | 4/15 | 5/13 | 6/19 |
| Team meeting and data review schedule | 8/24 |  | 10/13 | 11/17 | 12/15 | 1/19 | 2/16 | 3/16 | 4/20 | 5/18 | 6/22 |
| Complete the walkthrough prep for the Tiered Fidelity Inventory |  |  |  |  | 1/19-22 |  |  |  |  |  |  |
| Complete the Tiered Fidelity Inventory |  |  |  |  |  |  |  | 3/17 |  |  |  |
| Administer School Climate Surveys |  |  |  | 11/1-20 |  |  |  |  |  |  |  |
| Share data with students, staff, & caregivers |  |  |  |  | 12/18 |  |  |  |  |  | 6/3 |
| Present at BOE meeting |  |  |  |  |  |  |  |  |  | 5/21 |  |

| Teaching Norms | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Deliver Instruction on the school norms & area level actions Link to folder: |  | 9/3-9/5 |  |  | 12/8 |  |  | 3/9 |  |  |  |
| Deliver instruction on related SEL skills Link to folder: |  |  | 10/5 | 11/2 |  | 1/4 | 2/1 |  | 4/5 | 5/3 |  |
| Booster Events | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| Competition |  |  |  |  | 12/1-12/22 |  |  | 3/1-3/31 |  |  |  |
| Pause for a Cause |  |  |  | 11/1-11/5 |  |  | 2/21-2/25 |  | 4/12-4/16 |  |  |
| Reverse Week |  |  | 10/26-10/30 |  |  |  |  |  |  | 5/3-5/7 |  |
| End of year celebration |  |  |  |  |  |  |  |  |  |  | 6/8 |
| Messaging with Caregivers | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| Display table at school events |  | 9/17 |  |  | 12/17 |  | 2/19 |  | 4/20 |  |  |
| Newsletter column |  |  |  | 11/16 |  |  | 2/15 |  |  | 5/3 |  |
| Flyer, brochure, or other product distribution to families | 9/4 |  | 10/5 |  |  | 1/4 |  | 3/22 |  |  |  |
| Website posting | 8/27 |  |  |  |  |  |  |  |  |  |  |
| Social media post | 9/30 | 10/30 | 11/30 | 12/21 | 1/29 | 2/26 | 3/31 | 3/30 | 4/30 | 5/31 | 6/14 |

| Prepare Staff to Implement | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PD to get staff ready for the start of the year | 8/28 |  |  |  |  |  |  |  |  |  |  |
| Micro learning PD on new topics & practices |  |  | 10/12-10/16 |  | 12/7-12/11 |  | 2/8-2/12 |  | 4/5-4/9 |  |  |
| Implementation refreshers (reminder at staff meetings, eblasts, etc.) |  | 9/21 | 10/19 | 11/23 |  | 1/4 | 2/15 | 3/15 | 4/12 |  |  |
| Feedback & Input Routines | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| Staff input question at staff meeting |  |  | 10/8 | 11/12 | 12/10 | 1/14 | 2/11 | 3/12 | 4/15 |  |  |
| Student input routine |  |  |  | 11/17-11/18 |  |  |  | 3/16-3/17 |  |  |  |
| Caregiver input routine |  |  |  | 11/17-11/18 |  |  |  | 3/16-3/17 |  |  |  |
| Yearly Maintenance & Sustaining | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June |
| Update rollout materials | X |  |  |  |  |  |  |  | X | X | X |
| Arrange for new team members to receive training |  | X | X |  |  | X | X |  |  |  |  |
| Review and update the Implementation Manual and Procedure Documents | X |  |  |  |  |  |  |  |  | X | X |
| Send your PBSIS coach an updated team member contact list |  | X |  |  |  |  |  |  |  |  |  |
| Review and if needed update the matrix and posters |  |  |  |  |  |  |  |  |  |  |  |
| Update the Annual Planning Calendar |  |  |  |  |  |  |  |  |  |  |  |
| Register 3 team members to attend the Leadership Forum |  |  |  |  | X | X |  | Last wk in March |  |  |  |